## E1.1 Partial ex.
Stakeholder | Information Needed | Requirement? | Timeframe or Deadline | Priority | Product | Format | Responsible Staff | Resources? | Follow-up Action, Monitoring
AmeriCorps program | Evidence for intervention to support financial investment | Yes | Recompetition- December, 2017 | High | Final evaluation report | Written report, PDF; | Final Evaluation Report: External evaluator; dissemination: staff grant writer | $5,000 for external evaluator for final evaluation report | Work w/ CNCS R&E office to complete summary brief and post on Evidence Exchange; Discuss results with program officer

## E1.2 Complete ex.
Stakeholder | Information Needed | Requirement? | Timeframe or Deadline | Priority | Product | Format | Responsible Staff | Resources? | Follow-up Action, Monitoring
AmeriCorps program | Evidence for intervention | Yes | Recompetition- December, 2017 | High | Final evaluation report | Written report, PDF | Prep: External evaluator; dissemination: staff grant writer | $5,000 budgeted for external evaluator | Work w/ CNCS R&E office to complete summary brief and post on Evidence Exchange; Discuss results with program officer
Small foundation | Evidence for intervention to support financial investment | No | Recompetition- October, 2017 | High | Final evaluation report | Written report, PDF | Final Evaluation Report: External evaluator; dissemination: staff grant writer. | $5,000 for external evaluator for final evaluation report | Work w/ foundation to review conference presentation; Discuss results with foundation peer group
Program sites | Site level outcomes and feedback for improvement | No | Before 2017/2018 program year | Low | Executive summary; memo on site by site outcomes; improvements memo | Written documents, PDF | Executive summary: external evaluator; site by site memo: external evaluator; improvements memo- exec. director | $1,500 for external evaluator for exec. Summary; $7,000 for site by site memo; 15 hrs. for improvements memo | Review site results memo with each site (exec. Director and site supervisor) via conference call; schedule group conference call for sites to review improvements memo
Local bank partners | Partners' site level outcomes and plan for improvement | No | Before 2017/2018 program year | Medium | Executive summary; memo on site by site outcomes; improvements memo | Written documents, PDF | Executive summary: external evaluator; site by site memo: external evaluator; improvements memo- exec. director | - | Review site results memo with each sponsor (exec. Director, bank partner) via one-on-one conference call
Social service agency partner | Overall outcomes and plan for improvement | No | Before 2017/2018 program year | Medium | Executive summary; improvements memo | Written documents, PDF | Executive summary: external evaluator; improvements memo- exec. director | - | Review improvements memo with agency point of contact via conference call
FEC Board of Directors | Overall outcomes and plan for improvement | No | Before 2017/2018 program year | Low | Executive summary; improvements memo | Written documents, PDF | Executive summary: external evaluator; improvements memo- exec. director | - | Review improvements memo with board at next board meeting

## E1.3 Blank Template
Stakeholder | Information Needed | Requirement? | Timeframe or Deadline | Priority | Product | Format | Responsible Staff | Resources? | Follow-up Action, Monitoring