## Slide 1: Laying the Groundwork Before Your First Evaluation
AmeriCorps and NORC at the University of Chicago

## Slide 2: Learning Objectives
Understand five critical activities for your first grant cycle
Recognize how these activities lay the foundation for future evaluation work
Learn how to plan ahead to ensure that your program achieves key first-cycle milestones
Notes: -This is a new presentation that we haven’t yet presented as part of our evaluation core curriculum, so you’re in for a treat!
-The learning objectives are for you to:
-Understand five critical activities for your first grant cycle
-Recognize how these activities lay the foundation for future evaluation work
-And learn how to plan ahead to ensure that your program achieves key first-cycle milestones.

## Slide 3: Pre-Award Time Period
Do everything you can to set your program up for success in Year 1
Think through risks/threats to implementation and mitigate them
Begin to develop data collection systems
Begin to develop performance measurement plans
Notes: -Pre-award time period, 6-12 months before the program is expected to start.
-This is the time for you to do everything you can to set your program up for success in its first year.
-We understand that there will be variation in how programs use this “planning year” – some programs already exist and are just adding AmeriCorps members; some programs are in formula and can make refinements well in advance to set themselves up for success in competitive; some programs actually have planning grants (either commission formula or tribal grantees); some programs are brand new and may have varying levels of resources they can devote to planning for a grant they may or may not get, but if they can devote any time/resources to this, they should, and they should definitely use their time wisely from the time they learn they are funded to when they will begin enrolling members.
-Regardless, the planning period is the time to think through risks/threats to implementation and mitigate them.
-Since programs are expected to begin collecting data immediately in year 1, they should develop their data collection systems and performance measurement plans during the planning period to the extent that is realistic for them.

## Slide 4: Key Foundational Elements
Program design and implementation
Build and refine data collection systems
Performance measurement
Staff capacity and responsibilities
Evaluation planning
Become a learning organization
Notes: -We’re going to discuss these six activities: (1) program design and implementation, (2) building and refining data collection systems, (3) performance measurement, (4) staff capacity and responsibilities, (5) evaluation planning, and (6) becoming a learning organization.
-The activities we will discuss today are foundational and should not be afterthoughts in the first three years.
-It is important to budget money and staff time in the first 3 years for the activities we will be outlining in this workshop, just as you would later budget for evaluation activities.

## Slide 5: Your First Three Years: Program Activities Over Time
Notes: -All of these activities should be occurring during all three years of the first grant cycle, as shown on this slide.
-How much you focus on each will obviously ebb and flow over time, but it’s important to keep focused on all of them from the start.
-You want to set yourself up for success in the first grant cycle and beyond. Don’t wait until it’s too late to put these foundational elements in place!

## Slide 6: Building Evidence of Effectiveness
Building evidence of effectiveness
Stage 1: Identify a strong program design
Stage 5: Attain causal evidence of positive program outcomes
Stage 3: Assess program outcomes
Stage 2: Ensure effective implementation
Stage 4: Obtain evidence of positive program outcomes
Evidence Informed
Evidence Based
Notes: -As an agency, AmeriCorps continues to invest in a portfolio of programs reflecting a range of evidence, from evidence-informed to evidence-based. The diagram on this slide illustrates AmeriCorps’s approach to building evidence which emphasizes that evidence of effectiveness is built over time and falls along a continuum. Evidence should be appropriate for a program’s life cycle and investment of public dollars. This diagram shows different stages to situate a program’s cumulative body of evidence along an evidence continuum. Having a long-term research agenda will help programs progress from stage to stage along the evidence continuum in a resource efficient manner. Programs are not expected to follow the same linear path to building evidence along the continuum. Some programs may accumulate evidence from output performance measurement activities (stage 2) to having causal evidence of effectiveness from an RCT/QED (stage 5). Others may move from collecting output performance measurement data (stage 2) to having pre/post outcome data (stage 3). Programs may also go back and forth between stages as they refine and adjust their program models over time.
The key stages that a program goes through as they build their evidence base are shown in the diagram.
Stage 1: Identify a strong program design
Stage 2: Ensure effective implementation
Stage 3: Assess program outcomes
Stage 4: Obtain evidence of positive program outcomes
Stage 5: Attain causal evidence of positive program outcomes
-It’s important to note that these stages are not mutually exclusive and they do overlap, so consider the continuum to be a guide.
-For more information check out our new Evidence Continuum video on the Evaluation Resources page!
-The activities we discuss today will mostly fit into Stage 1 and Stage 2.

## Slide 7: 1. Program Design And Implementation
Goal: Improve program design and ensure effective implementation
Key components
  Refine logic model
  Assess implementation
  Conduct process evaluation
  Adjust program model as needed
Notes: -First, we will discuss program design and implementation. The goal of this activity is to improve your program design and ensure that your program is being implemented effectively.
-This means refining your logic model, assessing implementation, possibly conducting a more formal process evaluation, and using the resulting data to adjust your program model as needed.

## Slide 8: Refine Your Logic Model
Make sure your “model” is actually a model
Achieve shared agreement about what the model is and is not
Ensure all pieces of the model are plausibly connected
Notes: -Your program’s logic model is much more than just filling out the boxes. The logic model should clearly explain all the inputs and activities involved in running your program, and it should clearly lay out the outcomes you expect to achieve.
-A well-defined program model is specific and complete – it leaves little room for question or interpretation about how your program operates and what it intends to achieve.
-It is critical to understand (and minimize) variation in implementation unless there is a good reason for it.
-The weaker or less well-defined the program model is, the more difficult it is to ensure effective implementation. A poorly defined program model is also very difficult to evaluate down the road.
-As you refine your logic model, you want to discuss it with all relevant stakeholders and ensure that everyone is on the same page about what the program model is, and what it isn’t.
-You also want to ensure that all the pieces of the model are connected, and connected in a plausible and achievable way.

## Slide 9: Assessing Your Theory Of Change
 | Indicate to what extent each statement is true. |  |  | 
 | Not at all true | Somewhat true | True | Not applicable
Theory of Change |  |  |  | 
There is a coherent, logical program theory. Strategies and activities are designed to address a clearly identified and defined problem or need. There is a logical connection between the program strategies and activities and the intended outcomes or desired changes. Goals and objectives are articulated and attainable with the available resources. (The program has a logic model.) |  |  |  | 
Program participation is clearly defined and distinguishable from nonparticipation. There is no ambiguity about who is in the program and who is not. |  |  |  | 
There is a shared understanding among program leadership and staff about the core elements of the program and the context in which the program operates. |  |  |  | 
There is agreement across the program leadership and staff as to what the expected program outcomes are. |  |  |  | 
Clear Time Frame for the Program |  |  |  | 
The intervention has a clearly defined timeframe. |  |  |  | 
There is a reasonable and shared expectation around the timeframe for when observable/measurable outcomes in the short, intermediate or long term will occur. |  |  |  | 
Impact Evaluability Assessment Tool. Source: https://www.americorps.gov/sites/default/files/document/2015_09_03_ImpactEvaluabilityAssessmentTool_ORE.pdf, “Conducting a Needs or Readiness Assessment”.
Notes: -One of your handouts is the Impact Evaluability Assessment Tool, which we will discuss in more depth later in the presentation. Here we have highlighted the sections of the tool related to the theory of change and the program’s timeframe. This is on page 3 of your handout.
-This tool can serve as a guide as you refine your logic model. Think about the questions posed here:
-Is there a coherent, logical program theory?
-Are strategies and activities logically connected to the intended outcomes and desired changes?
-Is program participation clearly defined?
-Is there a shared understanding among all stakeholders about the core elements of the program and how it
operates, and what the expected outcomes are?
-Does the intervention have a clearly defined timeframe?
-Do all stakeholders have reasonable, shared expectations about when outcomes will occur?

## Slide 10: Assess Implementation
Implementing your program may lead to changes:
  In your logic model
    Some parts may not be plausible
    Some outcomes may not be realistic
  In how your program operates
Application logic model may be ideal  program model may change as it is implemented
  Important to document those changes so that you understand what you are actually doing
  Document any variation in implementation
Notes: -It is ok if implementing the program causes you to learn that some parts of your model are not plausible or some outcomes may not be realistic.
-For example, say that as you implement your program and collect data on that implementation process, and the data show that beneficiaries require a more intensive intervention (more one-on-one time with members, for instance) than originally expected. Your program may decide to spend more time serving fewer people than you originally proposed in your logic model, in order to achieve the desired comes.
-The logic model you submit in your application may be your best/ideal version. Know that that the model may change as it is implemented, and it is important to document those changes because you have to evaluate what you are actually doing
- For example, suppose that member time sheets show that sites are providing more training than expected. The program analyzes the data and learns that sites are having to provide follow-up training to address concepts that members did not master during their initial orientation. The training component of the program model can be changed to reflect that--either the program can standardize additional training across all sites or change what is offered at orientation.
-If there is variation in implementation that cannot be mitigated for whatever reason, it is important that you document that. Later on, when you plan an evaluation of your program, you will need to understand where and how implementation may be different and account for it in the evaluation design.

## Slide 11: Assessing Implementation
 | Indicate to what extent each statement is true. |  |  | 
 | Not at all true | Somewhat true | True | Not applicable
Program Implementation |  |  |  | 
If the program is based on a model or logical program theory, it is implemented with fidelity to that model and has a well-planned sequence of activities. |  |  |  | 
If the program is currently being adapted, it is being adapted using theory/systematically-obtained field-based knowledge, and along lines that can be quantified and documented. |  |  |  | 
Staff members are qualified and properly trained to operate the program. There are enough qualified staff members on site to implement the planned activities. |  |  |  | 
Frontline workers who deliver the services provided by the program have sufficient qualifications to execute the program. There are enough qualified frontline workers on site to successfully execute the program. |  |  |  | 
There are systems in place to track program implementation: There are procedures in place to determine if the target population is being served (referral system, intake process). Data that track service usage is collected (attendance lists, case management logs). Input is sought on a regular basis to understand how participants experience the services and to identify and address any problems in a timely manner. |    |    |    |   
Impact Evaluability Assessment Tool. Source: http://www.nationalservice.gov/resources/evaluation/planning-evaluation, “Conducting a Needs or Readiness Assessment”.
Notes: -Here again is another portion of the Impact Evaluability Assessment Tool, on page 4 of your handout, this time the section related to program implementation. As you assess implementation of your program, ask these questions:
-Is the program implemented with fidelity to the logic model?
-If the program is being adapted or revised, is that based on systematic data, and can the changes be documented?
-Are staff and members qualified and properly trained?
-Are there enough staff and members to successfully implement the program?
-Are you tracking service provision and service usage using appropriate data collection methods?

## Slide 12: 2. Build and Refine Data Collection Systems
Goal: Build systems to collect and manage high-quality program data
Key components
  Select data collection instruments
  Build data collection system
  Build data management system
  Obtain access to administrative data (if applicable)
  Ensure data quality
Notes: -Next, we’ll talk about building and refining data collection systems.
-From day one (or even before day one!) it is critically important that you have systems in place to collect and manage high-quality program data.
-You’ll need to figure out how you want to collect data, build data collection systems, put a system in place to manage the data, figure out how you will access other administrative data (if applicable), and in all cases ensure that the data you collect is high-quality.

## Slide 13: Data Collection System
First, examine logic model and think through data you need to collect
  Outputs
  Outcomes
  Implementation
  Other data beyond performance measures
Then, develop and test instruments
  Utilize existing resources
  Work with a professional to develop instruments that are valid and reliable
  Good instruments can also be used later for evaluation!
Notes: -First, you should look at your logic model and think through what data you need to collect—including data about outputs, outcomes, and implementation processes.
-In addition to output/outcome performance measurement data, you should be tracking implementation data. This includes output data other than beneficiaries served – for example, data about dosage/delivery of the intervention, data that makes it possible to ensure unduplicated counts, track multiple interventions provided to the same individual; demographic data; privacy concerns, etc.
-Where do you start? Think about how you want to be able access, analyze, and use the data and by look at your logic model. Begin with the end in mind.
-Instrument development: don’t just wing it. We have resources online about data collection for both performance measurement and evaluation. There are lots of high-quality instruments out there that you can use, and in most cases you will not have to create your own from scratch. You may want to work with an expert to develop instruments.
-Designing valid and reliable instruments means that in many cases they can also be used later for evaluation.

## Slide 14: Data Management System
Data management system should help you to:
  Store data
  Access data
  Analyze data
  Use data
Build (or buy) system to accomplish those goals
  Examples include: Efforts to Outcomes, Design Data, Outcomes Results System…
Notes: -You also need a data management system to store your data and allow you to access it and use it for program improvement, reporting, and decision making.
-This can be either a very costly endeavor or not.
-Low cost tools include Google docs, Microsoft Excel, and other widely available resources.
-Excel even has pretty sophisticated data analysis options that will accomplish most of your analytic needs at this stage.
-Eventually you will likely want to invest in a more sophisticated option, especially as your data storage needs increase and you require more complicated analytic tools.
-Talk to other grantees about systems that have worked well for them.
-We put some examples up here, but there are many options out there.

## Slide 15: Ensuring Data Quality
Elements of data quality:
  Valid: data mean what they are supposed to mean
  Complete: everyone reports full set of data
  Consistent: everyone uses same data collection methods
  Accurate: data are free from errors
  Verifiable: everyone follows standard practices and checks their data
Ensuring data quality means that you describe your program’s achievements in a trustworthy manner
Notes: -You need to ensure that the data you collect is high-quality. This means the data are:
-Valid: the data mean what they are supposed to mean
-Complete: everyone is reporting a full set of data
-Consistent: everyone uses the same data collection methods so that the same data are collected, in the same way
-Accurate: the data are free from errors
-Verifiable: Everyone follows the same standard practices and checks their data
-Data quality is very important. It means that you are describing your program’s achievements in a trustworthy manner.
-Check out Sarah Yue’s data quality course for more information

## Slide 16: 3. Performance Measurement
Goal: Collect and report performance measures; use results for program improvement
Key components
  Select performance measures
  Determine measurement frequency
  Adjust performance measures
  Execute performance management processes
  Connect performance management to evaluation
Notes: -All grantees are required to collect and report performance measures to AmeriCorps, but we really want you to be using performance measures data for program improvement.
-Performance measures are not a compliance exercise – they should be useful data that will help your program accomplish its goals.
-You will need to select appropriate performance measures, determine how often you will measure, adjust the measures over time as needed, use performance measurement data for program management, and eventually connect performance measurement and management processes to evaluation.

## Slide 17: Measure Selection and Adjustment
Select measures that reflect what your program is actually doing
Select measures you can use to understand how your program is working
Select targets that are ambitious yet achievable
Adjust measures annually if needed
Measures you collect and report for AmeriCorps grant
Other measures
Good performance measurement system!
Notes: -We know that many grantees think of performance measurement as just collecting data on the output(s)/outcome(s) in their grant, but really good performance measurement is much more than that.
-Especially with regard to implementation, you should start thinking about what other performance measures you need to be tracking: member enrollment/retention (already should be tracking for compliance purposes), member training outputs/outcomes, member supervision milestones, data on how the intervention is being implemented.
-Or, you may be tracking key performance measures but don’t know how that data can be used to understand and strengthen implementation, which is what we’ll talk about in the next slide.
-You want to set targets that are ambitious yet achievable, and you may need to adjust your measures or your targets over time.

## Slide 18: Performance Management
Do not just collect and report your performance measurement data – you need to use it!
Are goals being met?
Use data for program improvement
  Continuous feedback loop
  Programmatic decisions are
  grounded in data
  Strengthen implementation
Performance Measures Core Curriculum: http://www.nationalservice.gov/resources/performance-measurement
Select measures and set targets
Collect performance measures data
Analyze data
Identify programmatic improvements
Strengthen implementation
Notes: -You should not just be collecting and reporting performance measurement data to AmeriCorps – you need to use that data for program improvement.
-In order to achieve your program goals, you need to know if your goals are being met. One way to do that is by looking at performance measures data.
-Good measures can help you understand how your program is working. For example, let’s say that you want to understand more about program implementation, specifically member training. You could create a performance measure that looks at member knowledge gains at pre-service and in-service training sessions. These data can help you understand a key component of your program, member training, specifically how it is implemented. If targets are not achieved on this measure, you will know that member training is not being implemented as designed, and you should work to improve it so that targets are met.
-Performance management should be a continuous feedback loop, where you measure, analyze, identify improvements, make programmatic decisions that are grounded in data, and strengthen implementation as needed.
-For more information on performance measures, check out the Performance Measures Core Curriculum on the nationalservice.gov Resources page.

## Slide 19: Performance Management Example
AmeriCorps housing assistance program
  O5: Number of economically disadvantaged individuals, including homeless individuals, receiving housing services [Target = 500 calls]
  O11: Number of economically disadvantaged individuals, including homeless individuals, transitioned into safe, healthy, affordable housing [Target = 600]
Actuals: O5 = 900, O11 = 300
What’s going on?
  Individuals are calling the hotline multiple times
  Placement process takes longer than anticipated
Program response?
  Adjust call process – create a second number for repeat clients
  Adjust target for O11 to reflect reality of placement process
Notes: -Here’s an example of good performance management. A moderate sized AmeriCorps program operates a housing assistance hotline, where those in need of shelter can be connected with available housing units.
-The program selected the following Economic Opportunity performance measures: O5 (Number of economically disadvantaged individuals, including homeless individuals, receiving housing services) and O11 (Number of economically disadvantaged individuals, including homeless individuals, transitioned into safe, healthy, affordable housing).
-They set a target of fielding 500 calls during the project year, and placing 600 individuals in housing. At the end of the project year, the program reviews its data and discovers that they have exceeded their call target for O5 by 400 calls, fielding 900 calls during the project year. Additionally, they discover that they have only placed 300 individuals in housing.
-Reviewing the member call logs, used to track the number of calls fielded for O5, they find that individuals have called the hotline multiple times in order to secure their placement in housing. The program had anticipated that placement would be completed in the course of one call. Further, the program finds that the lower number of placements than the target of 600 for O11 reflects the fact that the placement process took longer than anticipated, requiring multiple touch points between the member and the client.
-In response, the program uses this data to make program improvements. First, the program will make adjustments to the call intake process to allow clients to call back multiple times through a separate number, preserving the hotline for first time callers and allowing for triage of cases. In addition, the program will readjust their target for O11 to more accurately reflect the time intensiveness of the placement process and demand for services.

## Slide 20: Connection to Evaluation
Good performance measurement can be the basis for future evaluation activities
  Outcome measures may be extended
  Instruments can be utilized
  Data can suggest interesting research questions
Performance measurement does not stop once evaluation begins
Notes: -Performance measures should be collected on an ongoing basis and compared to a target level, whereas an evaluation is designed to answer a specific research question about the goals of the intervention.
-Despite these differences, the two activities are closely linked and should be aligned.
-Well chosen performance measures can be the basis for future evaluation activities; for example, outcome measures can be extended or expanded upon, data collection instruments used for performance measures can often be used or adapted for evaluation, and reflecting on performance measures data can help when considering research questions for an evaluation.
-Importantly, performance measurement should be ongoing, all the time, every year. It does not stop once you begin your first evaluation.

## Slide 21: 4. Staff Capacity and Responsibilities
Goal: Build staff capacity to collect, manage, and utilize data
Key components
  Develop internal staff skills
  Assign responsibilities
  Engage external experts
  Become a learning organization
Notes: -From day one, you need to be thinking about how you can build your staff’s capacity to collect, manage, and utilize data.
-We acknowledge that this may require a change in both individual mindset – because not a lot of people go into national service because they want to measure things – and in organizational culture.
-However, the sooner you make staff development in this area a priority, the better you will fare down the line, and not just with AmeriCorps. This is a core competency for 21st century managers.
-Not only do you need to develop staff skills in these areas, but you need to assign responsibilities and sometimes engage external experts for more specialized or technical tasks.
-We will touch on this last point, becoming a learning organization, toward the end of the presentation.

## Slide 22: Internal Staff Capacity
Develop staff skills in data collection, management, and analysis
Know enough to know what you know, and know what you don’t know
Staff do not have to be experts, but they need to be educated and informed consumers
Assign responsibilities – someone has to take ownership of key tasks
Notes: -We don’t expect staff to be experts, but they should be reasonably capable. Staff need to know how to collect high-quality data and manage that data, and at least one person on staff should have basic analytic skills.
-It’s important for program managers to know what they know and what they don’t know, and what their staff know and don’t know. That can help you figure out in which areas you need to seek outside expertise, or where you can target staff development activities and resources.
-It’s also important that responsibilities for data tasks are clearly defined and assigned. Key tasks need owners so that nothing is missed or overlooked.
-Staff can check out the Evaluation and Performance Measurement Core Curricula, both available online on the Resources page.

## Slide 23: Identify and Work with External Experts
Utilize external experts for
  Data collection instruments
  Complicated analysis
  Questions about measurement
  Evaluation
Consider consultants, pro bono experts, cooperative extension, universities
Talk to other programs and stakeholders
Notes: -For some technical or complicated data tasks, you’ll want to engage external experts.
-Experts can be particularly helpful when you are designing data collection instruments, conducting complicated analyses, or when you have questions about measurement or evaluation.
-Tap into all available resources. Think about finding expertise through cooperative extension programs or universities, volunteer pro bono experts, your board, or consultants.
-Talk to other programs in your network – tap their brains, see where they have sought out help.

## Slide 24: Exercise: Evaluability Assessment Checklist
This checklist is a tool designed to help organizations assess and discuss a program’s readiness to participate in a rigorous impact evaluation. It can be used for assessment, planning, and communication purposes.
The focus areas covered in this checklist are organized into three broad content categories:
  Organization Readiness
  Program Readiness
  Evaluation Readiness
Each category addresses key elements of readiness. Readiness in all three areas covered is important for successful planning and implementation of an evaluation.
Notes: -Now we’re going to take a few minutes to have you start filling out the Impact Evaluability Assessment Tool.
-You can use this tool as a starting point/planning tool – we don’t expert you to have all the answers now, and some of the pages will only be relevant down the road when you start planning an evaluation.
-You could do the assessment annually, identify growth areas to focus on, make a plan, and assign responsibility for implementation of the plan, and assess again at the end of each year.
-There is a lot in here, so for now we will highlight some of the areas of focus that would be likely to be the best use of time for programs in first three years: theory of change, and implementation.
-Theory of change is on page 3
-Implementation is on page 4.

## Slide 25: 5. Evaluation Planning
Goal: Develop a plan for your first evaluation, which will occur in your second grant cycle (if not earlier).
Key components
  Select research questions
  Budget for evaluation
  Develop evaluation plan
  Make design decisions (process or impact, internal or external) based on grantee size
Notes: Facilitator notes: To recap, we’ve covered the first of four foundational elements, and now we’ll cover the remaining two: evaluation planning and becoming a learning org.
-For AmeriCorps State and National grantees, the first year of your competitive grant cycle should be used for developing an evaluation plan, which will be executed in the second year of your grant cycle. However, you can start slightly earlier if you want. It is also important to note that the evaluation requirement applies to grantees in their second grant cycle. Grantees in their very first grant cycle are not expected to have an evaluation plan, but may develop one in preparation for their second grant cycle.
Planning process has a few core components
  Select research questions. These should be questions that you are interested in learning about the program. They should also align with your program’s logic model and theory of change.
  Budget for evaluation
  Develop evaluation plan. This would need to be developed prior to your next grant cycle. You can develop this on your own, in consultation with an evaluator, or with other stakeholders such as your State Commission (if relevant).
  Make design decisions. It is important to note that the design selected may be pre-determined by the size of your program. That is, size is based on the average level of funding received each year from AmeriCorps during your three-year grant cycle. If you receive less than $500,000 on average per year, you are considered a small grantee and thus have flexibility in the design option you choose. However, if you received more than $500,000 on average per year, you would be considered large and would be required to conduct an impact evaluation. There are ways for large grantees to be exempt from this requirement (i.e., Alternative Evaluation Approach (AEA)). More information about evaluation designs and AEAs are discussed in more detail in the “How to Write an Evaluation Plan” and “Overview of Evaluation Designs” slides on the Evaluation Resources page on the AmeriCorps website.
-We will provide an overview of each of these components in this section of the presentation, however, there are also courses available on the Evaluation Resources page that will dive into these topics in much more detail.

## Slide 26: Develop Research Questions
Research questions are a list of questions grantees want to learn about their program
Research questions should be:
  Clear, specific, and well-defined
  Focus on a program or program component
  Measureable by the evaluation
  Appropriate for the design proposed
  Aligned with your logic model
Notes: One of the fist steps taken as you plan any evaluation is to develop research questions
Research questions are a list of questions that you anticipate being able to answer at the end of the evaluation.
  They focus the evaluation and provide important parameters for the evaluation design
  Research questions should test part of your TOC and map back to your LM.
  There are a few things to remember when creating your RQs:
    Clear, specific, and well-defined so they can be thoroughly answered after completing the other evaluation activities (e.g., instrument development, data collection, analysis, etc.).
    Also, need to focus on a program or program component.
      As AC grantees, make sure your eval focuses on the AC component of your program, in order for it to meet our evaluation requirements.
    It’s also important that your RQs be measurable by the evaluation, because they eventually need to be answered by your evaluation activities. That is, you should confirm that the data you collect for the evaluation will answer each research question.
    You will need to ensure that the research questions are appropriate for the design proposed. For instance, an impact evaluation includes a comparison or control group. Therefore, the research question should be phrased such that its clear that changes in the program beneficiaries will be compared to the changes experienced by a group not receiving the program’s services.
    Finally, RQs need to be aligned with your program’s logic model.
The research questions development process is a great time to engage stakeholders and gives a chance to get buy in and increase a feeling of ownership in the evaluation.
Creating research questions that follow these guidelines sets your evaluation up for success and helps manage internal and external expectations for the evaluation. If you would like more guidance about developing research questions, you may review the “Developing Research Questions for Evaluation” slides on the Evaluation Resources page on the AmeriCorps website.

## Slide 27: Budget For Evaluation
In general, evaluation budgets should be:
  Commensurate with stakeholder expectations and involvement
  Appropriate for the research design used and key questions to be answered
  Adequate for ensuring quality and rigor
  In line with the level of program and organizational resources available
Budgeting for evaluation is a smart strategic investment
Notes: Facilitator notes: In general, evaluation budgets should:
Reflect the expectations of stakeholders, particularly in terms of scope, duration, and level of rigor of the evaluation. Any requirements or mandated components as a condition of funding are also important here. For example, AmeriCorps State and National grantees receiving over $500k are required to conduct an external impact evaluation covering at least one program year. The use of an external evaluator and the methods needed to implement a comparison or control group design, for example, both bring their own particular cost requirements. So you can see that design requirements, scope of the evaluation, and who will be conducting the evaluation will affect the final budget. The evaluation budget should also reflect any stakeholder investment, be it financial or in another form such as time or technical assistance.
Evaluation budgets should also be appropriate for the research design used and the key research questions you want to answer. Certain evaluation methods or techniques, like primary data collection, simply cost more to execute than others. Relatedly, some key research questions will require different levels of investment, depending on their scope and the depth with which you want to answer them.
Budgets should also be of sufficient size to ensure that your evaluation will be high quality and rigorous. Underfunding may result in design choices that jeopardize the integrity of your evaluation. It can also lead to last minute workarounds, shortcuts, and quick fixes taken in the midst of your evaluation that can seriously impact the results produced.
Finally, an evaluation budget should reflect the financial, human capital, and other resources your program or organization has. For example, consider what kind of data collection systems you currently have in place and what you can plan to build for the future.
-Evaluation can provide critical insight into your program. We feel strongly that program evaluation goes beyond meeting requirements and provides important information for program management, decision-making, and improvement. We view evaluation as an smart strategic investment in improving your program, and ultimately, as a stepping stone to serving more beneficiaries more effectively.

## Slide 28: Write An Evaluation Plan
Written document that details all he evaluation steps and activities you plan to conduct
Dynamic tool (i.e., a living document) that should be continually updated as you plan and develop each aspect of the evaluation
Evaluation Plan Outline
Theory of change
Scope of the evaluation
Evaluation outcome(s) of interest
Research questions
Evaluation design
Sampling methods
Data collection
Analysis plan
Evaluator qualifications
Timeline
Budget
Notes: -A key activity in eval planning is formalizing the details of your evaluation in an evaluation plan.
-An evaluation plan is a written document that provides detail on all the evaluation’s steps and activities.
- Can be rel. short, a few pgs., or quite long, depending on the level of detail needed/desired.
- Important to record all info here b/c plan serves as a guide AND an accountability tool. Can be v. important when working with ext. eval or stakeholders.
Dynamic tool that is continually updated as the evaluation is planned and developed. Keep in mind that you can start a draft plan as soon as you like, steps are not linear. However, AmeriCorps State and National grantees are expected to obtain approval of their plan by the end of their first year of their grant cycle. Any significant changes made to the evaluation plan may need to undergo an additional round of review and approval.
An evaluation plan should include the following items. [read slide]
    I. Theory of change
    II. Scope of the evaluation
    III. Evaluation outcome(s) of interest
    IV. Research questions
    V. Evaluation design
    VI. Sampling methods
    VII. Data collection
    VIII. Analysis plan
    IX. Evaluator qualifications
    X. Timeline
    XI. Budget
-Again, we have an entire Evaluation Core Curriculum class on developing an evaluation plan, so this slide just briefly shows the key components of a well-developed evaluation plan.

## Slide 29: 6. Becoming A Learning Organization
A learning organization:
  Reflects on past successes and challenges
  Uses data to inform decision making
  Makes adjustments to programs and processes based on data
  Is not afraid to question assumptions
  Thinks strategically about how to improve
  Builds evidence of effectiveness
  Sets a research agenda for the future
Notes:   Last foundational element to be aware of in 1st 3 years: the concept of learning organizations. Start to implement steps to becoming one.
  A learning organization is an organization that creates, acquires, and transfers knowledge, and modifies its behavior to reflect new insights.
    Remain relevant, effective b/c can continuously improve their programs based on data.
    Data needed to continuously improve are readily available through performance measurement and program evaluation. Ideally you are doing both.
  By engaging in perf. Msmt and strategic program evaluation, you can collect the data you need to
    Remain competitive in a scarce funding environment,
    Justify increases in scale, scope, and reach,
    Demonstrate accountability to your stakeholders
    Build an evidence base demonstrating program efficacy
    The key takeaway here is that by doing PM and eval, you are enhancing your capacity to make data driven decisions, and hopefully to improve your services.

## Slide 30: Milestones
By the end of your first grant cycle, you should have:
  Refined your program and ensured effective implementation
  Built and refined data collection systems
  Utilized accurate performance measures
  Built staff capacity and defined responsibilities
  Prepared a plan for your first evaluation
  Become a learning organization
  And hopefully you’ve also had some fun!
Notes: -We’ve covered the 6 foundational elements, and to recap, by the end of your first grant cycle you should have met these key milestones:
-Refined your program and ensured it is being implemented effectively
-Built, tested, and refined your data collection systems
-Collected high-quality performance measure data and used that data for program improvement
-Develop staff capacity and assigned responsibilities for data tasks
-Prepared your first evaluation plan
-And begun the process of becoming a learning organization
If you’ve been able to make good progress on these foundational elements, you’ll be set up for success in coming grant cycles.

## Slide 31: Exercise: Laying the Foundation for Your Program
Notes: For this exercise, we are assuming you are all in your first grant cycle, at some point (or you have just seen the light and want to get up to speed on eval).
  Take the next 10-15 min. to go through this worksheet and write down 2-3 activities that you’ve done or are planning to do in this grant cycle for each of the 5 elements listed here
  The idea is that this worksheet can be a roadmap for you to follow.
  If you’re a brand new grantee in your first year, be aspirational. Think about what you want to do over the next 3 years, and how you want to go about that.
  If you’re in your 2nd or 3rd year, write down what you may already be doing currently, then think about the next year or two.

## Slide 32: Resources on Evaluation
Go to the Evaluation Resources page for more information:
https://americorps.gov/grantees-sponsors/evaluation-resources
Other courses available:
How to Develop a Program Logic Model
Overview of Evaluation Designs
How to Write an Evaluation Plan
Budgeting for Evaluation
Data Collection for Evaluation
Asking the Right Research Questions
Managing an External Evaluation
And more!
Notes: -For more information on evaluation, please go to the National Service Evaluation Resources page

## Slide 33: Questions?

## Slide 34: Thank you!
To contact the Office of Research and Evaluation: evaluation@cns.gov